## Slide 1: Global-to-Local GLOBIOM: Status
Michiel van Dijk
Interim presentation (10/05/2017)

## Slide 2: Objective
Develop a methodology (‘pipeline’) to prepare GLOBIOM for local (=subnational) analysis
Focus on improvement of land cover and land use maps (input side)
Apply this to Zambezi and Indus river basins in the context of the ISWEL project

## Slide 3: Features
Consistent – one approach that can be used for any subnational study
Bottom up – incorporating national agricultural statistics, household surveys and land cover information wherever possible
Coded – coded in R and GAMS for easy implementation and reproducibility
Documented – fully documented so that it can be reproduced in other projects

## Slide 4: Methodology to allocate agricultural area
Household surveys
Subnational statistics
Land cover maps
Harmonistation
County report
FAOSTAT
Downscaling
Simu land use map

## Slide 5: Country-level outputs
Land cover map
Land use map
Agricultural statistics at adm2 level
Country report
  Data sources
  Maps
  Data tables
  Comparison with FAOSTAT

## Slide 6: Status: Malawi case-study
Data collection and cleaning
  Completed
Data processing
  R scripts to analyse and harmonise data (nearly) completed
  Standard country report coded
Downscaling (in GAMS)
  In process
Documentation
  In process

## Slide 7: Zambezi river basin: Administrative regions versus simus

## Slide 8: Zambezi river basin: Land cover versus simus

## Slide 9: ISWEL: Proposed planning
May 2017: Prepare GLOBIOM for Zambezi (& Indus) analysis
May 2017: Finalise first complete version of Global-tot-local Globiom procedure (with application to MWI)
May-September 2017: Improve GLOBIOM with irrigation module – link with CWM
June-August 2017: Apply Global-to-local procedure to all Zambezi (&Indus) countries
June-August 2017: Test GLOBIOM with new data + case-study paper
September-December 2017: Conduct Zambezi (& Indus) analysis with GLOBIOM